## Project Overview
WTC Digital Signage Upgrade — Project Overview
Westfield ¦ 2026-04-01 ¦ ANC Proposal Engine
PROJECT INFORMATION
| Client | Westfield
| Project Name | WTC Digital Signage Upgrade
| Location | New York, NY
| Date Created | 2026-04-01
| Currency | USD
| Environment | Indoor
| Union Labor | No
| Bond Required | No
| Number of Displays | 24
FINANCIAL PARAMETERS
| LED Hardware Margin | 15%
| Install / Services Margin | 15%
| Engineering Margin | 15%
| Equipment Margin | 15%
| CMS Margin | 15%
| Bond Rate | N/A
| Tax Rate | Per zone (editable on MA)
| Tariff Rate | Per zone (editable on MA)
SUMMARY TOTALS
| Total Cost | 3647667.24
| Total Selling Price | 4212889.83
| Project Margin $ | 565222.59
| Project Margin % | 13%
| DOCUMENT TOTAL | 4212889.83

## Margin Analysis
WTC Digital Signage Upgrade — Margin Analysis
Westfield ¦ 2026-04-01 ¦ ANC Proposal Engine
| Zone / Category | Cost | Selling Price | Margin $ | Margin %
| Underpass 1 — Underpass 1-4, WTC |  | Selling Price
| LED Hardware | 34909.51 | 41070.01 | 6160.5 | 15%
| Structural Materials | 2088.75 | 2457.35 | 368.6 | 15%
| Structural Labor & LED Installation | 8703.13 | 10238.98 | 1535.85 | 15%
| Electrical & Data | 8703.13 | 10238.98 | 1535.85 | 15%
| PM / General Conditions / Travel | 20882.35 | 24567.47 | 3685.12 | 15%
| Engineering & Permits | 4705.88 | 5536.33 | 830.45 | 15%
| SUBTOTAL | 79992.75 | 92766.89 | 12774.14 | 13.77%
| TAX | 0 | 0 | 0 |  | 0%
| BOND | 0 | 0 | 0 |  | 0%
| TARIFF | 0 | 0 | 0 |  | 0%
| GRAND TOTAL | 79992.75 | 92766.89 | 12774.14 | 13.77%
| Underpass 2 — Underpass 1-4, WTC |  | Selling Price
| LED Hardware | 68046.11 | 80054.25 | 12008.14 | 15%
| Structural Materials | 4102.5 | 4826.47 | 723.97 | 15%
| Structural Labor & LED Installation | 17093.75 | 20110.29 | 3016.54 | 15%
| Electrical & Data | 17093.75 | 20110.29 | 3016.54 | 15%
| PM / General Conditions / Travel | 20882.35 | 24567.47 | 3685.12 | 15%
| Engineering & Permits | 4705.88 | 5536.33 | 830.45 | 15%
| SUBTOTAL | 131924.34 | 152572.17 | 20647.83 | 13.53%
| TAX | 0 | 0 | 0 |  | 0%
| BOND | 0 | 0 | 0 |  | 0%
| TARIFF | 0 | 0 | 0 |  | 0%
| GRAND TOTAL | 131924.34 | 152572.17 | 20647.83 | 13.53%
| Underpass 3 — Underpass 1-4, WTC |  | Selling Price
| LED Hardware | 68046.11 | 80054.25 | 12008.14 | 15%
| Structural Materials | 4102.5 | 4826.47 | 723.97 | 15%
| Structural Labor & LED Installation | 17093.75 | 20110.29 | 3016.54 | 15%
| Electrical & Data | 17093.75 | 20110.29 | 3016.54 | 15%
| PM / General Conditions / Travel | 20882.35 | 24567.47 | 3685.12 | 15%
| Engineering & Permits | 4705.88 | 5536.33 | 830.45 | 15%
| SUBTOTAL | 131924.34 | 152572.17 | 20647.83 | 13.53%
| TAX | 0 | 0 | 0 |  | 0%
| BOND | 0 | 0 | 0 |  | 0%
| TARIFF | 0 | 0 | 0 |  | 0%
| GRAND TOTAL | 131924.34 | 152572.17 | 20647.83 | 13.53%
| Underpass 4 — Underpass 1-4, WTC |  | Selling Price
| LED Hardware | 134265.3 | 157959.18 | 23693.88 | 15%
| Structural Materials | 6907.5 | 8126.47 | 1218.97 | 15%
| Structural Labor & LED Installation | 28781.25 | 33860.29 | 5079.04 | 15%
| Electrical & Data | 28781.25 | 33860.29 | 5079.04 | 15%
| PM / General Conditions / Travel | 20882.35 | 24567.47 | 3685.12 | 15%
| Engineering & Permits | 4705.88 | 5536.33 | 830.45 | 15%
| SUBTOTAL | 224323.53 | 259474.86 | 35151.33 | 13.55%
| TAX | 0 | 0 | 0 |  | 0%
| BOND | 0 | 0 | 0 |  | 0%
| TARIFF | 0 | 0 | 0 |  | 0%
| GRAND TOTAL | 224323.53 | 259474.86 | 35151.33 | 13.55%
| Concourse — Concourse, WTC |  | Selling Price
| LED Hardware | 845677.52 | 994914.73 | 149237.21 | 15%
| Structural Materials | 48536.25 | 57101.47 | 8565.22 | 15%
| Structural Labor & LED Installation | 202234.38 | 237922.8 | 35688.42 | 15%
| Electrical & Data | 202234.38 | 237922.8 | 35688.42 | 15%
| PM / General Conditions / Travel | 20882.35 | 24567.47 | 3685.12 | 15%
| Engineering & Permits | 4705.88 | 5536.33 | 830.45 | 15%
| SUBTOTAL | 1324270.76 | 1526801.71 | 202530.95 | 13.26%
| TAX | 0 | 0 | 0 |  | 0%
| BOND | 0 | 0 | 0 |  | 0%
| TARIFF | 0 | 0 | 0 |  | 0%
| GRAND TOTAL | 1324270.76 | 1526801.71 | 202530.95 | 13.27%
| T4-B1 (6-9) — T4-B1, WTC |  | Selling Price
| LED Hardware | 82785.77 | 97395.02 | 14609.25 | 15%
| Structural Materials | 4995 | 5876.47 | 881.47 | 15%
| Structural Labor & LED Installation | 20812.5 | 24485.29 | 3672.79 | 15%
| Electrical & Data | 20812.5 | 24485.29 | 3672.79 | 15%
| PM / General Conditions / Travel | 20882.35 | 24567.47 | 3685.12 | 15%
| Engineering & Permits | 4705.88 | 5536.33 | 830.45 | 15%
| SUBTOTAL | 154994 | 179138.59 | 24144.59 | 13.48%
| TAX | 0 | 0 | 0 |  | 0%
| BOND | 0 | 0 | 0 |  | 0%
| TARIFF | 0 | 0 | 0 |  | 0%
| GRAND TOTAL | 154994 | 179138.59 | 24144.59 | 13.48%
| T4-B2 (10-18) — T4-B2, WTC |  | Selling Price
| LED Hardware | 205655.43 | 241947.56 | 36292.13 | 15%
| Structural Materials | 11238.75 | 13222.06 | 1983.31 | 15%
| Structural Labor & LED Installation | 46828.13 | 55091.92 | 8263.79 | 15%
| Electrical & Data | 46828.13 | 55091.92 | 8263.79 | 15%
| PM / General Conditions / Travel | 20882.35 | 24567.47 | 3685.12 | 15%
| Engineering & Permits | 4705.88 | 5536.33 | 830.45 | 15%
| SUBTOTAL | 336138.67 | 388240.91 | 52102.24 | 13.42%
| TAX | 0 | 0 | 0 |  | 0%
| BOND | 0 | 0 | 0 |  | 0%
| TARIFF | 0 | 0 | 0 |  | 0%
| GRAND TOTAL | 336138.67 | 388240.91 | 52102.24 | 13.42%
| T4 Lobby Elevator — T4 Lobby Elevator, WTC |  | Selling Price
| LED Hardware | 139342.57 | 163932.44 | 24589.87 | 15%
| Structural Materials | 7222.5 | 8497.06 | 1274.56 | 15%
| Structural Labor & LED Installation | 30093.75 | 35404.41 | 5310.66 | 15%
| Electrical & Data | 30093.75 | 35404.41 | 5310.66 | 15%
| PM / General Conditions / Travel | 20882.35 | 24567.47 | 3685.12 | 15%
| Engineering & Permits | 4705.88 | 5536.33 | 830.45 | 15%
| SUBTOTAL | 232340.8 | 268709.18 | 36368.38 | 13.53%
| TAX | 0 | 0 | 0 |  | 0%
| BOND | 0 | 0 | 0 |  | 0%
| TARIFF | 0 | 0 | 0 |  | 0%
| GRAND TOTAL | 232340.8 | 268709.18 | 36368.38 | 13.53%
| T2-B1M Screen 20 — T2-B1M, WTC |  | Selling Price
| LED Hardware | 39872 | 46908.24 | 7036.24 | 15%
| Structural Materials | 2392.5 | 2814.71 | 422.21 | 15%
| Structural Labor & LED Installation | 9968.75 | 11727.94 | 1759.19 | 15%
| Electrical & Data | 9968.75 | 11727.94 | 1759.19 | 15%
| PM / General Conditions / Travel | 20882.35 | 24567.47 | 3685.12 | 15%
| Engineering & Permits | 4705.88 | 5536.33 | 830.45 | 15%
| SUBTOTAL | 87790.23 | 101747.09 | 13956.86 | 13.72%
| TAX | 0 | 0 | 0 |  | 0%
| BOND | 0 | 0 | 0 |  | 0%
| TARIFF | 0 | 0 | 0 |  | 0%
| GRAND TOTAL | 87790.23 | 101747.09 | 13956.86 | 13.72%
| T2-B1M Screen 21 — T2-B1M, WTC |  | Selling Price
| LED Hardware | 28714.71 | 33782.01 | 5067.3 | 15%
| Structural Materials | 1713.75 | 2016.18 | 302.43 | 15%
| Structural Labor & LED Installation | 7140.63 | 8400.74 | 1260.11 | 15%
| Electrical & Data | 7140.63 | 8400.74 | 1260.11 | 15%
| PM / General Conditions / Travel | 20882.35 | 24567.47 | 3685.12 | 15%
| Engineering & Permits | 4705.88 | 5536.33 | 830.45 | 15%
| SUBTOTAL | 70297.95 | 81602.53 | 11304.58 | 13.85%
| TAX | 0 | 0 | 0 |  | 0%
| BOND | 0 | 0 | 0 |  | 0%
| TARIFF | 0 | 0 | 0 |  | 0%
| GRAND TOTAL | 70297.95 | 81602.53 | 11304.58 | 13.85%
| T2-B1M Screen 22 — T2-B1M, WTC |  | Selling Price
| LED Hardware | 19348.52 | 22762.96 | 3414.44 | 15%
| Structural Materials | 1147.5 | 1350 | 202.5 | 15%
| Structural Labor & LED Installation | 4781.25 | 5625 | 843.75 | 15%
| Electrical & Data | 4781.25 | 5625 | 843.75 | 15%
| PM / General Conditions / Travel | 20882.35 | 24567.47 | 3685.12 | 15%
| Engineering & Permits | 4705.88 | 5536.33 | 830.45 | 15%
| SUBTOTAL | 55646.75 | 64730.65 | 9083.9 | 14.03%
| TAX | 0 | 0 | 0 |  | 0%
| BOND | 0 | 0 | 0 |  | 0%
| TARIFF | 0 | 0 | 0 |  | 0%
| GRAND TOTAL | 55646.75 | 64730.65 | 9083.9 | 14.03%
| New Path Hall Option 1 — New Path Hall, WTC |  | Selling Price
| LED Hardware | 223369.54 | 262787.69 | 39418.15 | 15%
| Structural Materials | 12315 | 14488.24 | 2173.24 | 15%
| Structural Labor & LED Installation | 51312.5 | 60367.65 | 9055.15 | 15%
| Electrical & Data | 51312.5 | 60367.65 | 9055.15 | 15%
| PM / General Conditions / Travel | 20882.35 | 24567.47 | 3685.12 | 15%
| Engineering & Permits | 4705.88 | 5536.33 | 830.45 | 15%
| SUBTOTAL | 363897.77 | 420209.14 | 56311.37 | 13.4%
| TAX | 0 | 0 | 0 |  | 0%
| BOND | 0 | 0 | 0 |  | 0%
| TARIFF | 0 | 0 | 0 |  | 0%
| GRAND TOTAL | 363897.77 | 420209.14 | 56311.37 | 13.4%
| New Path Hall Option 2 — New Path Hall, WTC |  | Selling Price
| LED Hardware | 284022.11 | 334143.66 | 50121.55 | 15%
| Structural Materials | 15483.75 | 18216.18 | 2732.43 | 15%
| Structural Labor & LED Installation | 64515.63 | 75900.74 | 11385.11 | 15%
| Electrical & Data | 64515.63 | 75900.74 | 11385.11 | 15%
| PM / General Conditions / Travel | 20882.35 | 24567.47 | 3685.12 | 15%
| Engineering & Permits | 4705.88 | 5536.33 | 830.45 | 15%
| SUBTOTAL | 454125.35 | 524323.94 | 70198.59 | 13.39%
| TAX | 0 | 0 | 0 |  | 0%
| BOND | 0 | 0 | 0 |  | 0%
| TARIFF | 0 | 0 | 0 |  | 0%
| GRAND TOTAL | 454125.35 | 524323.94 | 70198.59 | 13.39%
ADDITIONAL COST CENTERS
| CMS (Content Management System) | 0 | 0 | 0 | 15%
| Scoring System | 0 | 0 | 0 | 15%
| Venue Services | 0 | 0 | 0 | 15%
| Game Clock | 0 | 0 | 0 | 15%
| Pitch Clocks | 0 | 0 | 0 | 15%
| OES / MIS / Timing | 0 | 0 | 0 | 15%
| DMX / Misc Equipment | 0 | 0 | 0 | 15%
| BASE BID GRAND TOTAL | 3647667.24 | 4212889.83 | 565222.59 | 13%

## Budget Summary
WTC Digital Signage Upgrade — Budget Summary
Westfield ¦ 2026-04-01 ¦ By Category
| Category | Cost | Selling Price | Margin $ | Margin % | Price / SqFt
| LED Hardware (all displays) | 2174055.2 | 2557712 | 383656.8 | 15% | 325.89
| Structural Materials | 122246.25 | 143819.12 | 21572.87 | 15% | 18.32
| Structural Labor & LED Installation | 509359.4 | 599246.35 | 89886.95 | 15% | 76.35
| Electrical & Data | 509359.4 | 599246.35 | 89886.95 | 15% | 76.35
| PM / General Conditions / Travel | 271470.55 | 319377.12 | 47906.57 | 15%
| Engineering & Permits | 61176.44 | 71972.28 | 10795.84 | 15%
| CMS (Content Management System) | 0 | 0 | 0 | 15%
| Scoring System | 0 | 0 | 0 | 15%
| Venue Services | 0 | 0 | 0 | 15%
| Game Clock | 0 | 0 | 0 | 15%
| Pitch Clocks | 0 | 0 | 0 | 15%
| OES / MIS / Timing | 0 | 0 | 0 | 15%
| DMX / Misc Equipment | 0 | 0 | 0 | 15%
| SUBTOTAL | 3647667.24 | 4212889.83 | 565222.59 | 13% | 546.79
| TAX | 0 | 0 | 0 | 0%
| BOND | 0 | 0 | 0 | 0%
| GRAND TOTAL | 3647667.24 | 4212889.83 | 565222.59 | 13% | 546.79

## LED Cost Sheet
WTC Digital Signage Upgrade — LED Cost Sheet
[20 empty] | LED Margin Override → | 15%
Display | RFP H (ft) | RFP W (ft) | RFP NITs | Vendor | Product | Pitch | H (ft) | W (ft) | H (px) | W (px) | Qty | Total SqFt | Product NITs | Service | $/SqFt | Display Cost | Processor | Shipping | Total Cost | Margin % | Selling Price | ANC Margin | Weight (lbs) | Total Power (W) | BTU/hr
Underpass 1 — Underpass 1-4, WTC | 6.3 | 18.11 |  | Yaham | Yaham Corona C2.5-MIP Indoor | 2.5mm | 6.3 | 18.11 | 768 | 2208 | 1 | 114.09 | 2000 | front | 291.44 | 33250.16 | 518.45 | 1140.9 | 34909.51 | 13.77% | 92766.89 | 12774.14 | 558 | 4140 | 14126
Underpass 2 — Underpass 1-4, WTC | 7.48 | 29.92 |  | Yaham | Yaham Corona C2.5-MIP Indoor | 2.5mm | 7.48 | 29.92 | 912 | 3648 | 1 | 223.8 | 2000 | front | 291.44 | 65223.83 | 584.28 | 2238 | 68046.11 | 13.53% | 152572.17 | 20647.83 | 1094 | 8121 | 27709
Underpass 3 — Underpass 1-4, WTC | 7.48 | 29.92 |  | Yaham | Yaham Corona C2.5-MIP Indoor | 2.5mm | 7.48 | 29.92 | 912 | 3648 | 1 | 223.8 | 2000 | front | 291.44 | 65223.83 | 584.28 | 2238 | 68046.11 | 13.53% | 152572.17 | 20647.83 | 1094 | 8121 | 27709
Underpass 4 — Underpass 1-4, WTC | 12.6 | 29.92 |  | Yaham | Yaham Corona C2.5-MIP Indoor | 2.5mm | 12.6 | 29.92 | 1536 | 3648 | 1 | 376.99 | 2000 | front | 291.44 | 109869.21 | 20626.19 | 3769.9 | 134265.3 | 13.55% | 259474.86 | 35151.33 | 1842 | 13680 | 46676
Concourse — Concourse, WTC | 9.45 | 280.31 |  | Yaham | Yaham Corona C2.5-MIP Indoor | 2.5mm | 9.45 | 280.31 | 1152 | 34175 | 1 | 2648.93 | 2000 | front | 291.44 | 771998.86 | 47189.36 | 26489.3 | 845677.52 | 13.26% | 1526801.71 | 202530.95 | 12945 | 96124 | 327975
T4-B1 (6-9) — T4-B1, WTC | 7.87 | 8.66 |  | Yaham | Yaham Corona C2.5-MIP Indoor | 2.5mm | 7.87 | 8.66 | 960 | 1056 | 4 | 272.62 | 2000 | front | 291.42 | 79446 | 613.57 | 2726.2 | 82785.77 | 13.48% | 179138.59 | 24144.59 | 1332 | 9893 | 33755
T4-B2 (10-18) — T4-B2, WTC | 7.87 | 8.66 |  | Yaham | Yaham Corona C2.5-MIP Indoor | 2.5mm | 7.87 | 8.66 | 960 | 1056 | 9 | 613.39 | 2000 | front | 291.42 | 178753.5 | 20768.03 | 6133.9 | 205655.43 | 13.42% | 388240.91 | 52102.24 | 2997 | 22259 | 75948
T4 Lobby Elevator — T4 Lobby Elevator, WTC | 71.6 | 5.5 |  | Yaham | Yaham Corona C2.5-MIP Indoor | 2.5mm | 71.6 | 5.5 | 8729 | 671 | 1 | 393.8 | 2000 | front | 291.44 | 114768.29 | 20636.28 | 3938 | 139342.57 | 13.53% | 268709.18 | 36368.38 | 1924 | 14290 | 48757
T2-B1M Screen 20 — T2-B1M, WTC | 7.91 | 16.5 |  | Yaham | Yaham Corona C2.5-MIP Indoor | 2.5mm | 7.91 | 16.5 | 964 | 2012 | 1 | 130.52 | 2000 | front | 291.44 | 38038.49 | 528.31 | 1305.2 | 39872 | 13.72% | 101747.09 | 13956.86 | 638 | 4736 | 16159
T2-B1M Screen 21 — T2-B1M, WTC | 7.91 | 11.83 |  | Yaham | Yaham Corona C2.5-MIP Indoor | 2.5mm | 7.91 | 11.83 | 964 | 1442 | 1 | 93.58 | 2000 | front | 291.44 | 27272.76 | 506.15 | 935.8 | 28714.71 | 13.85% | 81602.53 | 11304.58 | 457 | 3396 | 11587
T2-B1M Screen 22 — T2-B1M, WTC | 7.91 | 7.91 |  | Yaham | Yaham Corona C2.5-MIP Indoor | 2.5mm | 7.91 | 7.91 | 964 | 964 | 1 | 62.57 | 2000 | front | 291.44 | 18235.28 | 487.54 | 625.7 | 19348.52 | 14.03% | 64730.65 | 9083.9 | 306 | 2271 | 7749
New Path Hall Option 1 — New Path Hall, WTC | 48 | 14 |  | Yaham | Yaham Corona C2.5-MIP Indoor | 2.5mm | 48 | 14 | 5852 | 1707 | 1 | 672 | 2000 | front | 291.44 | 195846.34 | 20803.2 | 6720 | 223369.54 | 13.4% | 420209.14 | 56311.37 | 3284 | 24385 | 83202
New Path Hall Option 2 — New Path Hall, WTC | 65 | 13 |  | Yaham | Yaham Corona C2.5-MIP Indoor | 2.5mm | 65 | 13 | 7925 | 1585 | 1 | 845 | 2000 | front | 291.44 | 246265.11 | 29307 | 8450 | 284022.11 | 13.39% | 524323.94 | 70198.59 | 4129 | 30663 | 104622
TOTAL (13 displays) | [11 empty] | 6671.09 |  |  |  | 1944191.66 | 163152.64 | 66710.9 | 2174055.2 | 15% | 2557712 | 383656.8 | 443324 | 3542380 | 12086601

## Tech Specs (Installers)
WTC Digital Signage Upgrade — LED Technical Specifications (No Pricing)
Technical specifications only — no pricing data. Safe for installer/subcontractor distribution.
Display Name | Qty | Pixel Pitch | Height (ft) | Width (ft) | Pixels H | Pixels W | Sq Ft | Brightness (nits) | Service | Environment | Weight (lbs) | Total Power (W) | Fiber Strands | BTU/hr
Underpass 1 — Underpass 1-4, WTC | 1 | 2.5mm | 6.3 | 18.11 | 768 | 2208 | 114.09 |  | front | indoor | 558 | 4140 | 4.24 | 14126
Underpass 2 — Underpass 1-4, WTC | 1 | 2.5mm | 7.48 | 29.92 | 912 | 3648 | 223.8 |  | front | indoor | 1094 | 8121 | 8.32 | 27709
Underpass 3 — Underpass 1-4, WTC | 1 | 2.5mm | 7.48 | 29.92 | 912 | 3648 | 223.8 |  | front | indoor | 1094 | 8121 | 8.32 | 27709
Underpass 4 — Underpass 1-4, WTC | 1 | 2.5mm | 12.6 | 29.92 | 1536 | 3648 | 376.99 |  | front | indoor | 1842 | 13680 | 14.01 | 46676
Concourse — Concourse, WTC | 1 | 2.5mm | 9.45 | 280.31 | 1152 | 34175 | 2648.93 |  | front | indoor | 12945 | 96124 | 98.42 | 327975
T4-B1 (6-9) — T4-B1, WTC | 4 | 2.5mm | 7.87 | 8.66 | 960 | 1056 | 272.62 |  | front | indoor | 1332 | 9893 | 10.14 | 33755
T4-B2 (10-18) — T4-B2, WTC | 9 | 2.5mm | 7.87 | 8.66 | 960 | 1056 | 613.39 |  | front | indoor | 2997 | 22259 | 22.81 | 75948
T4 Lobby Elevator — T4 Lobby Elevator, WTC | 1 | 2.5mm | 71.6 | 5.5 | 8729 | 671 | 393.8 |  | front | indoor | 1924 | 14290 | 14.64 | 48757
T2-B1M Screen 20 — T2-B1M, WTC | 1 | 2.5mm | 7.91 | 16.5 | 964 | 2012 | 130.52 |  | front | indoor | 638 | 4736 | 4.85 | 16159
T2-B1M Screen 21 — T2-B1M, WTC | 1 | 2.5mm | 7.91 | 11.83 | 964 | 1442 | 93.58 |  | front | indoor | 457 | 3396 | 3.48 | 11587
T2-B1M Screen 22 — T2-B1M, WTC | 1 | 2.5mm | 7.91 | 7.91 | 964 | 964 | 62.57 |  | front | indoor | 306 | 2271 | 2.32 | 7749
New Path Hall Option 1 — New Path Hall, WTC | 1 | 2.5mm | 48 | 14 | 5852 | 1707 | 672 |  | front | indoor | 3284 | 24385 | 24.97 | 83202
New Path Hall Option 2 — New Path Hall, WTC | 1 | 2.5mm | 65 | 13 | 7925 | 1585 | 845 |  | front | indoor | 4129 | 30663 | 31.4 | 104622

## Underpass 1 - Install
Project Name: WTC Digital Signage Upgrade
2026-04-01
Revised By: ANC Proposal Engine
Linked Margin Assignment
|  | Install Margin | 15%
|  | Electrical Margin | 15%
|  | ANC Margin | 15%
|  | Engineering and Permits | 15%
Underpass 1
| Height | Width | Total Sq. Ft | QTY
| 6.3 | 18.11 | 114.09 | 1
| Structural Materials: | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| FABRICATE SECONDARY STEEL SUBSTRUCTURE | 2088.75 | 0 | 0 | 0 | 0 | 2088.75 | 15% | 2457.35
| FABRICATE CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 2088.75 |  | 2457.35
| Structural Labor and LED Installation | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| REMOVAL AND DISPOSAL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL LED DISPLAYS | 8703.13 | 0 | 0 | 0 | 0 | 8703.13 | 15% | 10238.98
| INSTALL CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| HEAVY EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PM/GENERAL CONDITIONS/TRAVEL | 20882.35 | 0 | 0 | 0 | 0 | 20882.35 | 15% | 24567.47
| SUBTOTAL | [5 empty] | 29585.48 |  | 34806.45
| Electrical and Data - Materials and Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| ELECTRICAL MATERIALS | 8703.13 | 0 | 0 | 0 | 0 | 8703.13 | 15% | 10238.98
| DATA MATERIALS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| DATA LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUB PANEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| MISC | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 8703.13 |  | 10238.98
| Submittals, Engineering, and Permits | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| STRUCTURAL ENGINEERING | 4705.88 | 0 | 0 | 0 | 0 | 4705.88 | 15% | 5536.33
| STRUCTURAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL ENGINEERING | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PERMITS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4705.88 |  | 5536.33
| ZONE GRAND TOTAL | [5 empty] | 79992.75 |  | 92766.89

## Underpass 2 - Install
Project Name: WTC Digital Signage Upgrade
2026-04-01
Revised By: ANC Proposal Engine
Linked Margin Assignment
|  | Install Margin | 15%
|  | Electrical Margin | 15%
|  | ANC Margin | 15%
|  | Engineering and Permits | 15%
Underpass 2
| Height | Width | Total Sq. Ft | QTY
| 7.48 | 29.92 | 223.8 | 1
| Structural Materials: | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| FABRICATE SECONDARY STEEL SUBSTRUCTURE | 4102.5 | 0 | 0 | 0 | 0 | 4102.5 | 15% | 4826.47
| FABRICATE CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4102.5 |  | 4826.47
| Structural Labor and LED Installation | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| REMOVAL AND DISPOSAL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL LED DISPLAYS | 17093.75 | 0 | 0 | 0 | 0 | 17093.75 | 15% | 20110.29
| INSTALL CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| HEAVY EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PM/GENERAL CONDITIONS/TRAVEL | 20882.35 | 0 | 0 | 0 | 0 | 20882.35 | 15% | 24567.47
| SUBTOTAL | [5 empty] | 37976.1 |  | 44677.76
| Electrical and Data - Materials and Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| ELECTRICAL MATERIALS | 17093.75 | 0 | 0 | 0 | 0 | 17093.75 | 15% | 20110.29
| DATA MATERIALS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| DATA LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUB PANEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| MISC | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 17093.75 |  | 20110.29
| Submittals, Engineering, and Permits | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| STRUCTURAL ENGINEERING | 4705.88 | 0 | 0 | 0 | 0 | 4705.88 | 15% | 5536.33
| STRUCTURAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL ENGINEERING | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PERMITS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4705.88 |  | 5536.33
| ZONE GRAND TOTAL | [5 empty] | 131924.34 |  | 152572.17

## Underpass 3 - Install
Project Name: WTC Digital Signage Upgrade
2026-04-01
Revised By: ANC Proposal Engine
Linked Margin Assignment
|  | Install Margin | 15%
|  | Electrical Margin | 15%
|  | ANC Margin | 15%
|  | Engineering and Permits | 15%
Underpass 3
| Height | Width | Total Sq. Ft | QTY
| 7.48 | 29.92 | 223.8 | 1
| Structural Materials: | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| FABRICATE SECONDARY STEEL SUBSTRUCTURE | 4102.5 | 0 | 0 | 0 | 0 | 4102.5 | 15% | 4826.47
| FABRICATE CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4102.5 |  | 4826.47
| Structural Labor and LED Installation | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| REMOVAL AND DISPOSAL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL LED DISPLAYS | 17093.75 | 0 | 0 | 0 | 0 | 17093.75 | 15% | 20110.29
| INSTALL CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| HEAVY EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PM/GENERAL CONDITIONS/TRAVEL | 20882.35 | 0 | 0 | 0 | 0 | 20882.35 | 15% | 24567.47
| SUBTOTAL | [5 empty] | 37976.1 |  | 44677.76
| Electrical and Data - Materials and Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| ELECTRICAL MATERIALS | 17093.75 | 0 | 0 | 0 | 0 | 17093.75 | 15% | 20110.29
| DATA MATERIALS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| DATA LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUB PANEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| MISC | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 17093.75 |  | 20110.29
| Submittals, Engineering, and Permits | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| STRUCTURAL ENGINEERING | 4705.88 | 0 | 0 | 0 | 0 | 4705.88 | 15% | 5536.33
| STRUCTURAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL ENGINEERING | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PERMITS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4705.88 |  | 5536.33
| ZONE GRAND TOTAL | [5 empty] | 131924.34 |  | 152572.17

## Underpass 4 - Install
Project Name: WTC Digital Signage Upgrade
2026-04-01
Revised By: ANC Proposal Engine
Linked Margin Assignment
|  | Install Margin | 15%
|  | Electrical Margin | 15%
|  | ANC Margin | 15%
|  | Engineering and Permits | 15%
Underpass 4
| Height | Width | Total Sq. Ft | QTY
| 12.6 | 29.92 | 376.99 | 1
| Structural Materials: | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| FABRICATE SECONDARY STEEL SUBSTRUCTURE | 6907.5 | 0 | 0 | 0 | 0 | 6907.5 | 15% | 8126.47
| FABRICATE CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 6907.5 |  | 8126.47
| Structural Labor and LED Installation | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| REMOVAL AND DISPOSAL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL LED DISPLAYS | 28781.25 | 0 | 0 | 0 | 0 | 28781.25 | 15% | 33860.29
| INSTALL CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| HEAVY EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PM/GENERAL CONDITIONS/TRAVEL | 20882.35 | 0 | 0 | 0 | 0 | 20882.35 | 15% | 24567.47
| SUBTOTAL | [5 empty] | 49663.6 |  | 58427.76
| Electrical and Data - Materials and Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| ELECTRICAL MATERIALS | 28781.25 | 0 | 0 | 0 | 0 | 28781.25 | 15% | 33860.29
| DATA MATERIALS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| DATA LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUB PANEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| MISC | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 28781.25 |  | 33860.29
| Submittals, Engineering, and Permits | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| STRUCTURAL ENGINEERING | 4705.88 | 0 | 0 | 0 | 0 | 4705.88 | 15% | 5536.33
| STRUCTURAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL ENGINEERING | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PERMITS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4705.88 |  | 5536.33
| ZONE GRAND TOTAL | [5 empty] | 224323.53 |  | 259474.86

## Concourse - Install
Project Name: WTC Digital Signage Upgrade
2026-04-01
Revised By: ANC Proposal Engine
Linked Margin Assignment
|  | Install Margin | 15%
|  | Electrical Margin | 15%
|  | ANC Margin | 15%
|  | Engineering and Permits | 15%
Concourse
| Height | Width | Total Sq. Ft | QTY
| 9.45 | 280.31 | 2648.93 | 1
| Structural Materials: | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| FABRICATE SECONDARY STEEL SUBSTRUCTURE | 48536.25 | 0 | 0 | 0 | 0 | 48536.25 | 15% | 57101.47
| FABRICATE CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 48536.25 |  | 57101.47
| Structural Labor and LED Installation | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| REMOVAL AND DISPOSAL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL LED DISPLAYS | 202234.38 | 0 | 0 | 0 | 0 | 202234.38 | 15% | 237922.8
| INSTALL CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| HEAVY EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PM/GENERAL CONDITIONS/TRAVEL | 20882.35 | 0 | 0 | 0 | 0 | 20882.35 | 15% | 24567.47
| SUBTOTAL | [5 empty] | 223116.73 |  | 262490.27
| Electrical and Data - Materials and Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| ELECTRICAL MATERIALS | 202234.38 | 0 | 0 | 0 | 0 | 202234.38 | 15% | 237922.8
| DATA MATERIALS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| DATA LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUB PANEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| MISC | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 202234.38 |  | 237922.8
| Submittals, Engineering, and Permits | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| STRUCTURAL ENGINEERING | 4705.88 | 0 | 0 | 0 | 0 | 4705.88 | 15% | 5536.33
| STRUCTURAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL ENGINEERING | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PERMITS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4705.88 |  | 5536.33
| ZONE GRAND TOTAL | [5 empty] | 1324270.76 |  | 1526801.71

## T4-B1 (6-9) - Install
Project Name: WTC Digital Signage Upgrade
2026-04-01
Revised By: ANC Proposal Engine
Linked Margin Assignment
|  | Install Margin | 15%
|  | Electrical Margin | 15%
|  | ANC Margin | 15%
|  | Engineering and Permits | 15%
T4-B1 (6-9)
| Height | Width | Total Sq. Ft | QTY
| 7.87 | 8.66 | 272.62 | 4
| Structural Materials: | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| FABRICATE SECONDARY STEEL SUBSTRUCTURE | 4995 | 0 | 0 | 0 | 0 | 4995 | 15% | 5876.47
| FABRICATE CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4995 |  | 5876.47
| Structural Labor and LED Installation | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| REMOVAL AND DISPOSAL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL LED DISPLAYS | 20812.5 | 0 | 0 | 0 | 0 | 20812.5 | 15% | 24485.29
| INSTALL CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| HEAVY EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PM/GENERAL CONDITIONS/TRAVEL | 20882.35 | 0 | 0 | 0 | 0 | 20882.35 | 15% | 24567.47
| SUBTOTAL | [5 empty] | 41694.85 |  | 49052.76
| Electrical and Data - Materials and Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| ELECTRICAL MATERIALS | 20812.5 | 0 | 0 | 0 | 0 | 20812.5 | 15% | 24485.29
| DATA MATERIALS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| DATA LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUB PANEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| MISC | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 20812.5 |  | 24485.29
| Submittals, Engineering, and Permits | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| STRUCTURAL ENGINEERING | 4705.88 | 0 | 0 | 0 | 0 | 4705.88 | 15% | 5536.33
| STRUCTURAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL ENGINEERING | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PERMITS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4705.88 |  | 5536.33
| ZONE GRAND TOTAL | [5 empty] | 154994 |  | 179138.59

## T4-B2 (10-18) - Install
Project Name: WTC Digital Signage Upgrade
2026-04-01
Revised By: ANC Proposal Engine
Linked Margin Assignment
|  | Install Margin | 15%
|  | Electrical Margin | 15%
|  | ANC Margin | 15%
|  | Engineering and Permits | 15%
T4-B2 (10-18)
| Height | Width | Total Sq. Ft | QTY
| 7.87 | 8.66 | 613.39 | 9
| Structural Materials: | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| FABRICATE SECONDARY STEEL SUBSTRUCTURE | 11238.75 | 0 | 0 | 0 | 0 | 11238.75 | 15% | 13222.06
| FABRICATE CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 11238.75 |  | 13222.06
| Structural Labor and LED Installation | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| REMOVAL AND DISPOSAL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL LED DISPLAYS | 46828.13 | 0 | 0 | 0 | 0 | 46828.13 | 15% | 55091.92
| INSTALL CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| HEAVY EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PM/GENERAL CONDITIONS/TRAVEL | 20882.35 | 0 | 0 | 0 | 0 | 20882.35 | 15% | 24567.47
| SUBTOTAL | [5 empty] | 67710.48 |  | 79659.39
| Electrical and Data - Materials and Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| ELECTRICAL MATERIALS | 46828.13 | 0 | 0 | 0 | 0 | 46828.13 | 15% | 55091.92
| DATA MATERIALS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| DATA LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUB PANEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| MISC | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 46828.13 |  | 55091.92
| Submittals, Engineering, and Permits | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| STRUCTURAL ENGINEERING | 4705.88 | 0 | 0 | 0 | 0 | 4705.88 | 15% | 5536.33
| STRUCTURAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL ENGINEERING | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PERMITS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4705.88 |  | 5536.33
| ZONE GRAND TOTAL | [5 empty] | 336138.67 |  | 388240.91

## T4 Lobby Elevator - Install
Project Name: WTC Digital Signage Upgrade
2026-04-01
Revised By: ANC Proposal Engine
Linked Margin Assignment
|  | Install Margin | 15%
|  | Electrical Margin | 15%
|  | ANC Margin | 15%
|  | Engineering and Permits | 15%
T4 Lobby Elevator
| Height | Width | Total Sq. Ft | QTY
| 71.6 | 5.5 | 393.8 | 1
| Structural Materials: | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| FABRICATE SECONDARY STEEL SUBSTRUCTURE | 7222.5 | 0 | 0 | 0 | 0 | 7222.5 | 15% | 8497.06
| FABRICATE CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 7222.5 |  | 8497.06
| Structural Labor and LED Installation | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| REMOVAL AND DISPOSAL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL LED DISPLAYS | 30093.75 | 0 | 0 | 0 | 0 | 30093.75 | 15% | 35404.41
| INSTALL CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| HEAVY EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PM/GENERAL CONDITIONS/TRAVEL | 20882.35 | 0 | 0 | 0 | 0 | 20882.35 | 15% | 24567.47
| SUBTOTAL | [5 empty] | 50976.1 |  | 59971.88
| Electrical and Data - Materials and Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| ELECTRICAL MATERIALS | 30093.75 | 0 | 0 | 0 | 0 | 30093.75 | 15% | 35404.41
| DATA MATERIALS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| DATA LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUB PANEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| MISC | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 30093.75 |  | 35404.41
| Submittals, Engineering, and Permits | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| STRUCTURAL ENGINEERING | 4705.88 | 0 | 0 | 0 | 0 | 4705.88 | 15% | 5536.33
| STRUCTURAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL ENGINEERING | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PERMITS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4705.88 |  | 5536.33
| ZONE GRAND TOTAL | [5 empty] | 232340.8 |  | 268709.18

## T2-B1M Screen 20 - Install
Project Name: WTC Digital Signage Upgrade
2026-04-01
Revised By: ANC Proposal Engine
Linked Margin Assignment
|  | Install Margin | 15%
|  | Electrical Margin | 15%
|  | ANC Margin | 15%
|  | Engineering and Permits | 15%
T2-B1M Screen 20
| Height | Width | Total Sq. Ft | QTY
| 7.91 | 16.5 | 130.52 | 1
| Structural Materials: | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| FABRICATE SECONDARY STEEL SUBSTRUCTURE | 2392.5 | 0 | 0 | 0 | 0 | 2392.5 | 15% | 2814.71
| FABRICATE CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 2392.5 |  | 2814.71
| Structural Labor and LED Installation | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| REMOVAL AND DISPOSAL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL LED DISPLAYS | 9968.75 | 0 | 0 | 0 | 0 | 9968.75 | 15% | 11727.94
| INSTALL CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| HEAVY EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PM/GENERAL CONDITIONS/TRAVEL | 20882.35 | 0 | 0 | 0 | 0 | 20882.35 | 15% | 24567.47
| SUBTOTAL | [5 empty] | 30851.1 |  | 36295.41
| Electrical and Data - Materials and Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| ELECTRICAL MATERIALS | 9968.75 | 0 | 0 | 0 | 0 | 9968.75 | 15% | 11727.94
| DATA MATERIALS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| DATA LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUB PANEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| MISC | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 9968.75 |  | 11727.94
| Submittals, Engineering, and Permits | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| STRUCTURAL ENGINEERING | 4705.88 | 0 | 0 | 0 | 0 | 4705.88 | 15% | 5536.33
| STRUCTURAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL ENGINEERING | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PERMITS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4705.88 |  | 5536.33
| ZONE GRAND TOTAL | [5 empty] | 87790.23 |  | 101747.09

## T2-B1M Screen 21 - Install
Project Name: WTC Digital Signage Upgrade
2026-04-01
Revised By: ANC Proposal Engine
Linked Margin Assignment
|  | Install Margin | 15%
|  | Electrical Margin | 15%
|  | ANC Margin | 15%
|  | Engineering and Permits | 15%
T2-B1M Screen 21
| Height | Width | Total Sq. Ft | QTY
| 7.91 | 11.83 | 93.58 | 1
| Structural Materials: | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| FABRICATE SECONDARY STEEL SUBSTRUCTURE | 1713.75 | 0 | 0 | 0 | 0 | 1713.75 | 15% | 2016.18
| FABRICATE CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 1713.75 |  | 2016.18
| Structural Labor and LED Installation | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| REMOVAL AND DISPOSAL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL LED DISPLAYS | 7140.63 | 0 | 0 | 0 | 0 | 7140.63 | 15% | 8400.74
| INSTALL CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| HEAVY EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PM/GENERAL CONDITIONS/TRAVEL | 20882.35 | 0 | 0 | 0 | 0 | 20882.35 | 15% | 24567.47
| SUBTOTAL | [5 empty] | 28022.98 |  | 32968.21
| Electrical and Data - Materials and Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| ELECTRICAL MATERIALS | 7140.63 | 0 | 0 | 0 | 0 | 7140.63 | 15% | 8400.74
| DATA MATERIALS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| DATA LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUB PANEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| MISC | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 7140.63 |  | 8400.74
| Submittals, Engineering, and Permits | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| STRUCTURAL ENGINEERING | 4705.88 | 0 | 0 | 0 | 0 | 4705.88 | 15% | 5536.33
| STRUCTURAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL ENGINEERING | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PERMITS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4705.88 |  | 5536.33
| ZONE GRAND TOTAL | [5 empty] | 70297.95 |  | 81602.53

## T2-B1M Screen 22 - Install
Project Name: WTC Digital Signage Upgrade
2026-04-01
Revised By: ANC Proposal Engine
Linked Margin Assignment
|  | Install Margin | 15%
|  | Electrical Margin | 15%
|  | ANC Margin | 15%
|  | Engineering and Permits | 15%
T2-B1M Screen 22
| Height | Width | Total Sq. Ft | QTY
| 7.91 | 7.91 | 62.57 | 1
| Structural Materials: | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| FABRICATE SECONDARY STEEL SUBSTRUCTURE | 1147.5 | 0 | 0 | 0 | 0 | 1147.5 | 15% | 1350
| FABRICATE CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 1147.5 |  | 1350
| Structural Labor and LED Installation | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| REMOVAL AND DISPOSAL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL LED DISPLAYS | 4781.25 | 0 | 0 | 0 | 0 | 4781.25 | 15% | 5625
| INSTALL CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| HEAVY EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PM/GENERAL CONDITIONS/TRAVEL | 20882.35 | 0 | 0 | 0 | 0 | 20882.35 | 15% | 24567.47
| SUBTOTAL | [5 empty] | 25663.6 |  | 30192.47
| Electrical and Data - Materials and Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| ELECTRICAL MATERIALS | 4781.25 | 0 | 0 | 0 | 0 | 4781.25 | 15% | 5625
| DATA MATERIALS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| DATA LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUB PANEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| MISC | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4781.25 |  | 5625
| Submittals, Engineering, and Permits | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| STRUCTURAL ENGINEERING | 4705.88 | 0 | 0 | 0 | 0 | 4705.88 | 15% | 5536.33
| STRUCTURAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL ENGINEERING | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PERMITS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4705.88 |  | 5536.33
| ZONE GRAND TOTAL | [5 empty] | 55646.75 |  | 64730.65

## New Path Hall Option 1 - Instal
Project Name: WTC Digital Signage Upgrade
2026-04-01
Revised By: ANC Proposal Engine
Linked Margin Assignment
|  | Install Margin | 15%
|  | Electrical Margin | 15%
|  | ANC Margin | 15%
|  | Engineering and Permits | 15%
New Path Hall Option 1
| Height | Width | Total Sq. Ft | QTY
| 48 | 14 | 672 | 1
| Structural Materials: | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| FABRICATE SECONDARY STEEL SUBSTRUCTURE | 12315 | 0 | 0 | 0 | 0 | 12315 | 15% | 14488.24
| FABRICATE CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 12315 |  | 14488.24
| Structural Labor and LED Installation | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| REMOVAL AND DISPOSAL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL LED DISPLAYS | 51312.5 | 0 | 0 | 0 | 0 | 51312.5 | 15% | 60367.65
| INSTALL CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| HEAVY EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PM/GENERAL CONDITIONS/TRAVEL | 20882.35 | 0 | 0 | 0 | 0 | 20882.35 | 15% | 24567.47
| SUBTOTAL | [5 empty] | 72194.85 |  | 84935.12
| Electrical and Data - Materials and Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| ELECTRICAL MATERIALS | 51312.5 | 0 | 0 | 0 | 0 | 51312.5 | 15% | 60367.65
| DATA MATERIALS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| DATA LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUB PANEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| MISC | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 51312.5 |  | 60367.65
| Submittals, Engineering, and Permits | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| STRUCTURAL ENGINEERING | 4705.88 | 0 | 0 | 0 | 0 | 4705.88 | 15% | 5536.33
| STRUCTURAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL ENGINEERING | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PERMITS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4705.88 |  | 5536.33
| ZONE GRAND TOTAL | [5 empty] | 363897.77 |  | 420209.14

## New Path Hall Option 2 - Instal
Project Name: WTC Digital Signage Upgrade
2026-04-01
Revised By: ANC Proposal Engine
Linked Margin Assignment
|  | Install Margin | 15%
|  | Electrical Margin | 15%
|  | ANC Margin | 15%
|  | Engineering and Permits | 15%
New Path Hall Option 2
| Height | Width | Total Sq. Ft | QTY
| 65 | 13 | 845 | 1
| Structural Materials: | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| FABRICATE SECONDARY STEEL SUBSTRUCTURE | 15483.75 | 0 | 0 | 0 | 0 | 15483.75 | 15% | 18216.18
| FABRICATE CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| OTHER SCOPE ITEM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 15483.75 |  | 18216.18
| Structural Labor and LED Installation | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| REMOVAL AND DISPOSAL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| INSTALL LED DISPLAYS | 64515.63 | 0 | 0 | 0 | 0 | 64515.63 | 15% | 75900.74
| INSTALL CLADDING AND TRIM | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| HEAVY EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PM/GENERAL CONDITIONS/TRAVEL | 20882.35 | 0 | 0 | 0 | 0 | 20882.35 | 15% | 24567.47
| SUBTOTAL | [5 empty] | 85397.98 |  | 100468.21
| Electrical and Data - Materials and Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| ELECTRICAL MATERIALS | 64515.63 | 0 | 0 | 0 | 0 | 64515.63 | 15% | 75900.74
| DATA MATERIALS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| DATA LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUB PANEL | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| MISC | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 64515.63 |  | 75900.74
| Submittals, Engineering, and Permits | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | Selected | Additional Contingency | Total Cost | Install Margin | Selling Price
| STRUCTURAL ENGINEERING | 4705.88 | 0 | 0 | 0 | 0 | 4705.88 | 15% | 5536.33
| STRUCTURAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL ENGINEERING | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| ELECTRICAL CERTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| PERMITS | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0
| SUBTOTAL | [5 empty] | 4705.88 |  | 5536.33
| ZONE GRAND TOTAL | [5 empty] | 454125.35 |  | 524323.94

## Processor Count
WTC Digital Signage Upgrade — Processor Count
| Display | Width (px) | Height (px) | Ports | Ports (80%) | 8-bit Video | 8-bit (80%) | 10/12/HDR bit
| 660 Pro | 1920 | 1080 | 8 |  | 650000 | 455000 | 320000
| MCTRL4K | 3840 | 2160 | 16 |  | 650000 | 455000 | 320000
| H9 Enhanced | 7680 | 4320 | 20 |  | 1200000 | 960000 | 650000
DISPLAY PROCESSOR REQUIREMENTS
| Display | Width (px) | Height (px) | Qty | Total Pixels | Ports Needed | Processor Type | Processors Needed
| Underpass 1 | 0 | 0 | 1 | 1695744 | 3 | 660 Pro | 1
| Underpass 2 | 0 | 0 | 1 | 3326976 | 6 | 660 Pro | 1
| Underpass 3 | 0 | 0 | 1 | 3326976 | 6 | 660 Pro | 1
| Underpass 4 | 0 | 0 | 1 | 5603328 | 9 | MCTRL4K | 1
| Concourse | 0 | 0 | 1 | 39369600 | 61 | MCTRL4K | 4
| T4-B1 (6-9) | 0 | 0 | 4 | 4055040 | 7 | 660 Pro | 1
| T4-B2 (10-18) | 0 | 0 | 9 | 9123840 | 15 | MCTRL4K | 1
| T4 Lobby Elevator | 0 | 0 | 1 | 5857159 | 10 | MCTRL4K | 1
| T2-B1M Screen 20 | 0 | 0 | 1 | 1939568 | 3 | 660 Pro | 1
| T2-B1M Screen 21 | 0 | 0 | 1 | 1390088 | 3 | 660 Pro | 1
| T2-B1M Screen 22 | 0 | 0 | 1 | 929296 | 2 | 660 Pro | 1
| New Path Hall Option 1 | 0 | 0 | 1 | 9989364 | 16 | MCTRL4K | 1
| New Path Hall Option 2 | 0 | 0 | 1 | 12561125 | 20 | MCTRL4K | 2
| TOTAL |  |  |  | 99168104 | 161 |  | 17

## Bundle Equipment
WTC Digital Signage Upgrade — Processor & Equipment Breakdown
Editable — adjust component costs per display zone. Totals roll into Margin Analysis.
Category | Component | Cost | Qty | Total Cost | Margin | Selling Price | Margin $
Underpass 1 — Underpass 1-4, WTC
EQUIPMENT | Sending Card | 450 | 1 | 450 | 15% | 529.41 | 79.41
EQUIPMENT | Signal Cable Kit | 68.45 | 1 | 68.45 | 15% | 80.53 | 12.08
| Zone Subtotal |  |  | 518.45 |  | 609.94 | 91.49
Underpass 2 — Underpass 1-4, WTC
EQUIPMENT | Sending Card | 450 | 1 | 450 | 15% | 529.41 | 79.41
EQUIPMENT | Signal Cable Kit | 134.28 | 1 | 134.28 | 15% | 157.98 | 23.7
| Zone Subtotal |  |  | 584.28 |  | 687.39 | 103.11
Underpass 3 — Underpass 1-4, WTC
EQUIPMENT | Sending Card | 450 | 1 | 450 | 15% | 529.41 | 79.41
EQUIPMENT | Signal Cable Kit | 134.28 | 1 | 134.28 | 15% | 157.98 | 23.7
| Zone Subtotal |  |  | 584.28 |  | 687.39 | 103.11
Underpass 4 — Underpass 1-4, WTC
EQUIPMENT | Sending Card | 8400 | 1 | 8400 | 15% | 9882.35 | 1482.35
EQUIPMENT | Signal Cable Kit | 226.19 | 1 | 226.19 | 15% | 266.11 | 39.92
EQUIPMENT | Backup Video Processor | 12000 | 1 | 12000 | 15% | 14117.65 | 2117.65
| Zone Subtotal |  |  | 20626.19 |  | 24266.11 | 3639.92
Concourse — Concourse, WTC
EQUIPMENT | Sending Card | 33600 | 1 | 33600 | 15% | 39529.41 | 5929.41
EQUIPMENT | Signal Cable Kit | 1589.36 | 1 | 1589.36 | 15% | 1869.84 | 280.48
EQUIPMENT | Backup Video Processor | 12000 | 1 | 12000 | 15% | 14117.65 | 2117.65
| Zone Subtotal |  |  | 47189.36 |  | 55516.9 | 8327.54
T4-B1 (6-9) — T4-B1, WTC
EQUIPMENT | Sending Card | 450 | 1 | 450 | 15% | 529.41 | 79.41
EQUIPMENT | Signal Cable Kit | 163.57 | 1 | 163.57 | 15% | 192.44 | 28.87
| Zone Subtotal |  |  | 613.57 |  | 721.85 | 108.28
T4-B2 (10-18) — T4-B2, WTC
EQUIPMENT | Sending Card | 8400 | 1 | 8400 | 15% | 9882.35 | 1482.35
EQUIPMENT | Signal Cable Kit | 368.03 | 1 | 368.03 | 15% | 432.98 | 64.95
EQUIPMENT | Backup Video Processor | 12000 | 1 | 12000 | 15% | 14117.65 | 2117.65
| Zone Subtotal |  |  | 20768.03 |  | 24432.98 | 3664.95
T4 Lobby Elevator — T4 Lobby Elevator, WTC
EQUIPMENT | Sending Card | 8400 | 1 | 8400 | 15% | 9882.35 | 1482.35
EQUIPMENT | Signal Cable Kit | 236.28 | 1 | 236.28 | 15% | 277.98 | 41.7
EQUIPMENT | Backup Video Processor | 12000 | 1 | 12000 | 15% | 14117.65 | 2117.65
| Zone Subtotal |  |  | 20636.28 |  | 24277.98 | 3641.7
T2-B1M Screen 20 — T2-B1M, WTC
EQUIPMENT | Sending Card | 450 | 1 | 450 | 15% | 529.41 | 79.41
EQUIPMENT | Signal Cable Kit | 78.31 | 1 | 78.31 | 15% | 92.13 | 13.82
| Zone Subtotal |  |  | 528.31 |  | 621.54 | 93.23
T2-B1M Screen 21 — T2-B1M, WTC
EQUIPMENT | Sending Card | 450 | 1 | 450 | 15% | 529.41 | 79.41
EQUIPMENT | Signal Cable Kit | 56.15 | 1 | 56.15 | 15% | 66.06 | 9.91
| Zone Subtotal |  |  | 506.15 |  | 595.47 | 89.32
T2-B1M Screen 22 — T2-B1M, WTC
EQUIPMENT | Sending Card | 450 | 1 | 450 | 15% | 529.41 | 79.41
EQUIPMENT | Signal Cable Kit | 37.54 | 1 | 37.54 | 15% | 44.16 | 6.62
| Zone Subtotal |  |  | 487.54 |  | 573.57 | 86.03
New Path Hall Option 1 — New Path Hall, WTC
EQUIPMENT | Sending Card | 8400 | 1 | 8400 | 15% | 9882.35 | 1482.35
EQUIPMENT | Signal Cable Kit | 403.2 | 1 | 403.2 | 15% | 474.35 | 71.15
EQUIPMENT | Backup Video Processor | 12000 | 1 | 12000 | 15% | 14117.65 | 2117.65
| Zone Subtotal |  |  | 20803.2 |  | 24474.35 | 3671.15
New Path Hall Option 2 — New Path Hall, WTC
EQUIPMENT | Sending Card | 16800 | 1 | 16800 | 15% | 19764.71 | 2964.71
EQUIPMENT | Signal Cable Kit | 507 | 1 | 507 | 15% | 596.47 | 89.47
EQUIPMENT | Backup Video Processor | 12000 | 1 | 12000 | 15% | 14117.65 | 2117.65
| Zone Subtotal |  |  | 29307 |  | 34478.83 | 5171.83
EQUIPMENT GRAND TOTAL |  |  |  | 163152.64 |  | 191944.29 | 28791.65

## ANC Travel
WTC Digital Signage Upgrade — ANC Travel
| Travel - Installation | Cost | Quantity | Total Cost
| Hotel | 300 | 0 | 0
| Airfare | 1000 | 0 | 0
| Car | 125 | 0 | 0
| Per Diem | 100 | 0 | 0
| Bundled | 10000 | 0 | 0 | Account for freelancer
| Total |  |  | 0
| TOTAL | USD: |  | 0
| Travel - Commissioning | Cost | Quantity | Total Cost
| Hotel | 300 | 0 | 0
| Airfare | 1000 | 0 | 0
| Car | 125 | 0 | 0
| Per Diem | 100 | 0 | 0
| Bundled | 10000 | 0 | 0 | Account for freelancer
| Total |  |  | 0
| TOTAL | USD: |  | 0
| Game Support | Cost | Quantity | Total Cost
| Hotel | 300 | 0 | 0
| Airfare | 1000 | 0 | 0
| Car | 125 | 0 | 0
| Per Diem | 100 | 0 | 0
| Bundled | 10000 | 0 | 0 | Account for freelancer
| Game Day Support | 1500 | 0 | 0
| Total |  |  | 0
| TOTAL | USD: |  | 0

## CMS
WTC Digital Signage Upgrade — Content Management System
CMS Platform
All costs require project-specific pricing — update items below based on RFP requirements
| Category | Item | Cost | Quantity | Total Cost | Margin | Selling Price | Margin $
| PRIMARY | DESIGN & CONTROL SOFTWARE | 0 | 0 | 0 | 10% | 0 | 0
| PRIMARY | GRAPHICS PLAYBACK ENGINE | 0 | 0 | 0 | 10% | 0 | 0
| PRIMARY | IMAGE PROCESSING | 0 | 0 | 0 | 10% | 0 | 0
| PRIMARY | DEDICATED LED ROUTER / SWITCH | 0 | 0 | 0 | 10% | 0 | 0
| REDUNDANT | DESIGN & CONTROL SOFTWARE | 0 | 0 | 0 | 10% | 0 | 0
| REDUNDANT | GRAPHICS PLAYBACK ENGINE | 0 | 0 | 0 | 10% | 0 | 0
| REDUNDANT | IMAGE PROCESSING | 0 | 0 | 0 | 10% | 0 | 0
| STANDARD SERVICES | COMMISSIONING | 0 | 0 | 0 | 10% | 0 | 0
| STANDARD SERVICES | EVENT SUPPORT | 0 | 0 | 0 | 10% | 0 | 0
| STANDARD SERVICES | PROJECT MANAGEMENT | 0 | 0 | 0 | 10% | 0 | 0
|  | Integration Hardware | 0 | 0 | 0 | 10% | 0 | 0
|  | Integration Labor | 0 | 0 | 0 | 10% | 0 | 0
|  | Shipping | 0 | 0 | 0 | 10% | 0 | 0
|  | Travel | 0 | 0 | 0 | 10% | 0 | 0
|  | CMS TOTAL |  |  | 0 |  | 0 | 0
| TAX |  |  |  | 0
| BOND |  |  |  | 0
| SUB TOTAL | USD: |  |  | 0 |  | 0 | 0

## Scoring
WTC Digital Signage Upgrade — Scoring System
Scoring Platform
All costs require project-specific pricing — update items below based on RFP requirements
| Category | Item | Cost | Quantity | Total Cost | Margin | Selling Price | Margin $
| HARDWARE | SCORING CONTROLLER / SERVER | 0 | 0 | 0 | 10% | 0 | 0
| HARDWARE | OPERATOR WORKSTATION(S) | 0 | 0 | 0 | 10% | 0 | 0
| HARDWARE | SCOREBOARD INPUT DEVICES | 0 | 0 | 0 | 10% | 0 | 0
| HARDWARE | SHOT CLOCK / GAME CLOCK INTERFACE | 0 | 0 | 0 | 10% | 0 | 0
| HARDWARE | STATISTICS INTERFACE | 0 | 0 | 0 | 10% | 0 | 0
| SOFTWARE | SCORING SOFTWARE LICENSE | 0 | 0 | 0 | 10% | 0 | 0
| SOFTWARE | GRAPHICS / ANIMATION PACKAGE | 0 | 0 | 0 | 10% | 0 | 0
| SOFTWARE | STATISTICS INTEGRATION | 0 | 0 | 0 | 10% | 0 | 0
| SERVICES | COMMISSIONING | 0 | 0 | 0 | 10% | 0 | 0
| SERVICES | TRAINING | 0 | 0 | 0 | 10% | 0 | 0
| SERVICES | PROJECT MANAGEMENT | 0 | 0 | 0 | 10% | 0 | 0
|  | Integration Hardware | 0 | 0 | 0 | 10% | 0 | 0
|  | Integration Labor | 0 | 0 | 0 | 10% | 0 | 0
|  | Shipping | 0 | 0 | 0 | 10% | 0 | 0
|  | Travel | 0 | 0 | 0 | 10% | 0 | 0
|  | SCORING TOTAL |  |  | 0 |  | 0 | 0
| TAX |  |  |  | 0
| BOND |  |  |  | 0
| SUB TOTAL | USD: |  |  | 0 |  | 0 | 0

## Venue Services
WTC Digital Signage Upgrade — Venue Services
Multi-year service contract calculator
Contract Years | 3 | Editable service term
Year 1 Cost | 0 | Base annual contract value
Annual Escalation % | 3% | Applied to each renewal year
Margin % | 15% | Target service-contract margin
Year | Cost | Selling Price | Margin $ | Notes
Year 1 | 0 | 0 | 0 | Escalated annual term
Year 2 | 0 | 0 | 0 | Escalated annual term
Year 3 | 0 | 0 | 0 | Escalated annual term
| 0 | 0 | 0
| 0 | 0 | 0
VENUE SERVICES TOTAL | 0 | 0 | 0

## Additional Items
WTC Digital Signage Upgrade — Additional Non-LED Items
| Category | Item | Cost | Quantity | Total Cost | Margin | Selling Price | Margin $
| GAME CLOCK | Six-Digit Game Clocks | 0 | 1 | 0 | 15% | 0 | 0
| PITCH CLOCK | Pitch Clocks | 0 | 1 | 0 | 15% | 0 | 0
| OES / MIS | OES / MIS / Timing | 0 | 1 | 0 | 15% | 0 | 0
| MISC | DMX / Misc Equipment | 0 | 1 | 0 | 15% | 0 | 0
|  | ADDITIONAL ITEMS TOTAL |  |  | 0 |  | 0 | 0

## Resp Matrix
Project: WTC Digital Signage Upgrade
Date: 4/1/2026
Administrative | ANC | Purchaser
Provide accurate architectural, structural engineering, and AV drawings. |  | X
Provide Payment and Performance Bond. | NA
All required zoning, building, street or sidewalk permits. | NA
Shipping of all equipment to site. | X
Receive, unload, and inspect all new equipment upon arrival. | X
Provide safe storage of video equipment and control room. |  | X
Unobstructed access to equipment and control room. |  | X
Engineering & Submittals | ANC | Purchaser
Customer responsible to ensure existing structure supports new equipment. |  | X
Provide mechanical drawings, electrical drawings, and load calculations. | X
Engineering and certification for new equipment attachments. | X
Provide approval of all mechanical/electrical drawings. |  | X
Responsible to ensure structural integrity of existing conditions. |  | X
Physical Installation | ANC | Purchaser
ANC assumes all base building structure is provided by others. | Include Statement
ANC has included removal and disposal of existing equipment. |  | X
ANC assumes reasonable access will be provided to the work area. | Include Statement
Fabricate, deliver, and install support structure. | X
Provide & Install LED components. | X
Provide all required Floor/Site Protection. |  | X
Electrical & Data Installation | ANC | Purchaser
Submit electrical engineering drawings. | X
Provide primary power feed to each display location. |  | X
Provide secondary electrical panels and/or remote disconnects. |  | X
Furnish signal cables as specified by ANC. | X
Provide and install signal cable conduit. |  | X
Labor to pull signal cable. | X
Terminate signal cable at control system equipment. | X
Mount and install data patch panel. | X
Provide high speed internet connection to control room. |  | X
Control System | ANC | Purchaser
ANC has provided display processors only. | Include Statement
Provide climate controlled control room. |  | X
Supply static IP address five (5) days prior to installation. |  | X
Training | ANC | Purchaser
Provide appropriate on-site operation and maintenance training. | X
Provide sign off list for all training. | X
Perform one (1) day of maintenance training. | X
Perform final systems testing and commissioning. | X
General Conditions | ANC | Purchaser
ANC has provided a parts only warranty, excluding labor. | Include Statement
ANC has included installation pricing with prevailing labor rates. |  | X
ANC has not included bonding of any kind. | Include Statement
ANC has not included any tax in the proposal. | Include Statement
Shipping included in quoted pricing. | Include Statement

## P&L
WTC Digital Signage Upgrade — P&L
Project #: |  |  | 50/20/20/10
| PROJECTS BUDGET |  |  |  |  | CONTRACT BUDGET
| Revenue | Budgeted Cost | Margin |  |  | Revenue | Budgeted Cost
Base Contract | 4212889.83 | 3647667.24 | 565222.59 |  | TOTAL BASE CONTRACT | 4212889.83 | 3647667.24
TOTAL BASE CONTRACT | 4212889.83 | 3647667.24 | 565222.59
Change Orders
Total Change Order(s) Amount | 0 | 0 | 0
Grand Total | 4212889.83 | 3647667.24 | 565222.59
Cost Category | Revenue | Budget | Committed POs | Budget Remaining
LED | 0 | 1851611.09 | 0 | 1851611.09
Install | 0 | 631605.65 | 0 | 631605.65
Electrical | 0 | 509359.4 | 0 | 509359.4
ANC Travel | 0 | 195000 | 0 | 195000
Structural Engineering | 0 | 61176.44 | 0 | 61176.44
Electrical Engineering | 0 | 0 | 0 | 0
CMS | 0 | 0 | 0 | 0
Parts/Labor | 0 | 0 | 0 | 0
Tax | 0 | 0 | 0 | 0
Bond | 0 | 0 | 0 | 0
BASE CONTRACT TOTAL |  | 3647667.24 | 0 | 3647667.24

## Cash Flow
WTC Digital Signage Upgrade — Cash Flow
Payment Terms: 50/20/20/10
|  |  | Payment Phases | Contract Signed | Product Shipping | Substantial Completion | Sign Off
|  |  | Percentages | 50% | 20% | 20% | 10%
| Contract Award Date | TBD
| Scheduled Completion | TBD
| Revenue | Expenses | Gross Profit | Gross Profit % | Budget Tracking (+/-)
| 4212889.83 | 3647667.24 | 565222.59 | 13.42% | 0
Month |  |  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10
Revenue |  | Amount | Date Submitted
1 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue |  | 0

## PO's
WTC Digital Signage Upgrade — Purchase Orders
PO Number | Vendor | Title / Description | Original Contract Amount | Category
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## _Products (hidden)
10mm Mesh P10 (Nitxeon)
2.5mm Indoor (Nationstar MIP)
4mm Indoor (Nitxeon)
C1.2-MIP 1.2mm Indoor (Alt)
C1.8-MIP 1.8mm Indoor/VisiBowl (Alt)
LG LSCA015 1.5mm Indoor Fine Pitch
LG LSCA039 3.91mm Indoor Ceiling
LG LSCB025 2.5mm Indoor Wall
LG LSGA039 3.9mm Indoor Wall
Mesh P10 FM1921 3.9mm Indoor
Yaham Aura A10 Perimeter
Yaham Corona C10 Indoor
Yaham Corona C2.5-MIP Indoor
Yaham Corona C4 Indoor
Yaham Corona C6 Indoor
Yaham Halo H10T Fascia Indoor
Yaham Halo HO10T Fascia Outdoor
Yaham Halo HO6T Fascia Outdoor
Yaham Radiance R10 Outdoor
Yaham Radiance R2.5-MIP Outdoor
Yaham Radiance R4 Outdoor
Yaham Radiance R6 Outdoor
Yaham Radiance R8 Outdoor