## Sheet3
ID | BID PACKAGE | INSTALL YEAR | LEVEL | LOCATION | LED CMS RACK ROOM | LED HEADEND RACK ROOM | LED FIBER CONV RACK (IF REQUIRED) | CMS TYPE | LED CMS TYPE | DISPLAY SPECIFIC NOTES | IMAGE HEIGHT |  | IMAGE WIDTH |  | TOLERANCE | MAX HEIGHT | PIXEL PITCH | INDOOR / OUTDOOR | UNIFORM BRIGHTNESS | UNIFORM BRIGHTNESS | SERVICE
LED-GPL2-01 | 4 | 2026 | GPL LEVEL 2 | MPR - EAST WALL | AV/IT 2.5.130 | AV/IT 2.5.130 | N/A | TBD | - INPUTS FROM AV SYSTEM PER AV DRAWINGS. - INCLUDE (2) 12G-SDI INPUTS FOR IMAG INPUTS FROM VIDEO PRODUCTION SYSTEM | PROVIDE SYNC INPUT FROM VIDEO PRODUCTION SYSTEM. INTEGRATE CONTROL WITH 27 41 16 AV SYSTEM | 9 | 0 | 16 | 0 | 1% | -- | 1.2MM | INDOOR | 700 NITS | HDR | FRONT
LED-GPL2-02 | 4 | 2026 | GPL LEVEL 2 | MPR - NORTH WALL - EAST SIDE | AV/IT 2.5.130 | AV/IT 2.5.130 | N/A | TBD | - INPUTS FROM AV SYSTEM PER AV DRAWINGS. - INCLUDE (2) 12G-SDI INPUTS FOR IMAG INPUTS FROM VIDEO PRODUCTION SYSTEM | PROVIDE SYNC INPUT FROM VIDEO PRODUCTION SYSTEM. INTEGRATE CONTROL WITH 27 41 16 AV SYSTEM | 5 | 4 | 9 | 6 | 1% | -- | 1.2MM | INDOOR | 700 NITS | HDR | FRONT
LED-GPL2-03 | 4 | 2026 | GPL LEVEL 2 | MPR - NORTH WALL - WEST SIDE | AV/IT 2.5.130 | AV/IT 2.5.130 | N/A | TBD | - INPUTS FROM AV SYSTEM PER AV DRAWINGS. - INCLUDE (2) 12G-SDI INPUTS FOR IMAG INPUTS FROM VIDEO PRODUCTION SYSTEM | PROVIDE SYNC INPUT FROM VIDEO PRODUCTION SYSTEM. INTEGRATE CONTROL WITH 27 41 16 AV SYSTEM | 5 | 4 | 9 | 6 | 1% | -- | 1.2MM | INDOOR | 700 NITS | HDR | FRONT
LED-EXT.SW-101 | 6 | 2026 | N/A | SW CORNER | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) | CONTINUOUS WRAP-AROUND CORNER | 23 | 10 | 92 | 8 | 1% | -- | 8MM | OUTDOOR | 8000 NITS | HDR | FRONT
LED-EXT.E-103 | 6 | 2026 | N/A | EAST DISPLAY | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 20 | 10 | 30 | 2 | 1% | -- | 8MM | OUTDOOR | 8000 NITS | HDR | FRONT
LED-EXT.W-105 | 6 | 2026 | N/A | WEST DISPLAY | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 23 | 10 | 57 | 10 | 1% | -- | 8MM | OUTDOOR | 8000 NITS | HDR | FRONT
LED-EXT.S-106 | 6 | 2026 | N/A | SOUTH DISPLAY NEAR ENTRY | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) | DISPLAY IS AT PEDESTRIAN HEIGHT. BIDDER TO PROPOSE PHYSICAL PROTECTION | 7 | 0 | 22 | 8 | 1% | -- | 2.9MM | OUTDOOR | 4000 NITS | HDR | FRONT
LED-EXT.N-107 | 6 | 2026 | N/A | NORTH DISPLAY NEAR ENTRY | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) | DISPLAY IS AT PEDESTRIAN HEIGHT. BIDDER TO PROPOSE PHYSICAL PROTECTION | 6 | 0 | 15 | 3 | 1% |  | 2.9MM | OUTDOOR | 4000 NITS | HDR | FRONT
LED.EXT.SW-201 | 6 | 2026 | N/A | SW WMATA VESTIBULE INSIDE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) | DISPLAY REMAINS FOR BASE BID. 1:1 REPLACEMENT OF EXISTING LED ADD-ALT | 5 | 0 | 21 | 3 | 1% |  | 2.9MM | OUTDOOR | 3000 NITS | HDR | FRONT
LED.EXT.SW-202 | 6 | 2026 | N/A | SW WMATA VESTIBULE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) | DISPLAY REMAINS FOR BASE BID. 1:1 REPLACEMENT OF EXISTING LED IS ADD-ALT | 2 | 4 | 21 | 3 | 1% |  | 2.9MM | OUTDOOR | 3000 NITS | HDR | FRONT
LED.EXT.SW-203 | 6 | 2026 | N/A | SW WMATA VESTIBULE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) | DISPLAY REMAINS FOR BASE BID. 1:1 REPLACEMENT OF EXISTING LED IS ADD-ALT | 2 | 4 | 21 | 3 | 1% |  | 2.9MM | OUTDOOR | 3000 NITS | HDR | FRONT
LED.EXT.SW-204 | 6 | 2026 | N/A | SW WMATA VESTIBULE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) | DISPLAY REMAINS FOR BASE BID. 1:1 REPLACEMENT OF EXISTING LED IS ADD-ALT | 2 | 4 | 21 | 3 | 1% |  | 2.9MM | OUTDOOR | 3000 NITS | HDR | FRONT
LED.EXT.SW-205 | 6 | 2026 | N/A | SW WMATA VESTIBULE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) | DISPLAY REMAINS FOR BASE BID. 1:1 REPLACEMENT OF EXISTING LED IS ADD-ALT | 2 | 4 | 21 | 3 | 1% |  | 2.9MM | OUTDOOR | 3000 NITS | HDR | FRONT
LED-L1-01 | 6 | 2026 | MAIN CONCOURSE | SOUTH (F-STREET) ENTRY LOBBY, CEILING | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) | CURVED CEILING | 43 | 0 | 68 | 0 | 1% | -- | 1.9MM | INDOOR | 3000 NITS | HDR | FRONT
LED-L1-03 | 6 | 2027 | MAIN CONCOURSE | EAST (6th ST) PREMIUM ENTRY LOBBY, BEHIND GLASS | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) | INDOOR LED MESH - TRANSPARENT, 45-55% OPEN. DISPLAY IS EXCLUDED FROM BASE BID. ADD-ALT ONLY | 14 | 0 | 63 | 3 | 1% | -- | 3.9MM | INDOOR | 3000 NITS | HDR | FRONT
LED-L1-04 | 6 | 2027 | MAIN CONCOURSE | EAST (6th ST) PREMIUM ENTRY LOBBY, BEHIND GLASS | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) | INDOOR LED MESH - TRANSPARENT, 45-55% OPEN. DISPLAY IS EXCLUDED FROM BASE BID. ADD-ALT ONLY | 14 | 0 | 21 | 3 | 1% | -- | 3.9MM | INDOOR | 3000 NITS | HDR | FRONT
LED-C1-01 | 7 | 2027 | 100 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 6 | 0 | 12 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C1-02 | 7 | 2027 | 100 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 6 | 0 | 21 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C1-03 | 7 | 2027 | 100 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 6 | 0 | 8 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C1-04 | 7 | 2027 | 100 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 6 | 0 | 21 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C1-05 | 7 | 2027 | 100 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 6 | 0 | 12 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C1-06 | 7 | 2027 | 100 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 6 | 0 | 12 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C1-07 | 7 | 2027 | 100 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 10 | 0 | 70 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C1-08 | 7 | 2027 | 100 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 10 | 0 | 70 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C1-09 | 7 | 2027 | 100 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 10 | 0 | 70 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-VB-01 - LED-VB-06 | 7 | 2027 | 100 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) | VISIBOWL SOUTH LED DISPLAY SHALL BE UNINTERUPTED FROM EDGE TO EDGE, CONTINIUNG OVER THE VOMS. REFER TO ARCHITECTURAL DRAWINGS FOR EXACT DIMENSIONS AND SHAPE | -- | -- | -- | -- | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-VB-07 - LED-VB-09 | 7 | 2027 | 100 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) | VISIBOWL NORTH LED DISPLAY SHALL BE UNINTERUPTED FROM EDGE TO EDGE, CONTINIUNG OVER THE VOMS. REFER TO ARCHITECTURAL DRAWINGS FOR EXACT DIMENSIONS AND SHAPE | -- | -- | -- | -- | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C2-01 | 7 | 2027 | 200 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 30 | 0 | 6 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C2-02 | 7 | 2027 | 200 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 30 | 0 | 6 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C2-03 | 7 | 2027 | 200 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 21 | 0 | 6 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C2-04 | 7 | 2027 | 200 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 30 | 0 | 6 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C2-05 | 7 | 2027 | 200 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 30 | 0 | 6 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C2-06 | 7 | 2027 | 200 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 18 | 0 | 6 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C4-01 | 7 | 2027 | 400 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 21 | 0 | 6 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C4-02 | 7 | 2027 | 400 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 12 | 0 | 6 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C4-03 | 7 | 2027 | 400 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 12 | 0 | 6 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C4-04 | 7 | 2027 | 400 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 40 | 0 | 6 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C4-05 | 7 | 2027 | 400 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 12 | 0 | 6 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-C4-06 | 7 | 2027 | 400 LEVEL | MAIN CONCOURSE | P1 LED HEADEND | P1 LED HEADEND | BIDDER TO PROPOSE | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) |  | 21 | 0 | 6 | 0 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-GPL1-01 | 7 | 2027 | GPL LEVEL 2 | ATRIUM LED 1 | AV/IT 1.5.208 | AV/IT 1.5.208 | N/A | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) - MINIMUM (1) SPARE 4K HDMI INPUT PER DISPLAY |  | 11 | 8 | 20 | 2 | 1% | -- | 2.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-GPL1-02 | 7 | 2027 | GPL LEVEL 1 | ATRIUM LED 2 | AV/IT 1.5.208 | AV/IT 1.5.208 | N/A | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) - MINIMUM (1) SPARE 4K HDMI INPUT PER DISPLAY |  | 7 | 0 | 13 | 1 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LED-GPL1-04 | 7 | 2027 | GPL LEVEL 1 | ATRIUM LED 4 | AV/IT 1.5.208 | AV/IT 1.5.208 | N/A | TBD | -FULL SCREEN LED CMS (LIVE VIDEO, ADVERTISING, ANIMATIONS, GAME-IN-PROGRESS) - MINIMUM (1) SPARE 4K HDMI INPUT PER DISPLAY | DISPLAY IS LOCATED ACROSS AN EXPANSION JOINT. ATTACH LED TO ONE SIDE ONLY. | 7 | 0 | 13 | 1 | 1% | -- | 1.9MM | INDOOR | 700 NITS | HDR | FRONT
LEVELS:
EXT = EXTERIOR
P1 = PARKING LEVEL 1
E0 = EVENT LEVEL
MZ = MEZZANINE LEVEL
L1 = MAIN CONCOURSE
L2 = SUITE CONCOURSE
L3 = CLUB CONCOURSE
L4 = UPPER CONCOURSE
L6 = PRESS LEVEL
B# = BOWL LED
GPL1 = GALLERY PLACE LEVEL 1
GPL2 = GALLERY PLACE LEVEL 2
GENERAL NOTES:
1. FIELD VERIFY ALL DIMENSIONS FOR ALL LED DISPLAYS.
2. ADD-ALT OPTIONS SHALL INCLUDE ALL ELECTRICAL, DATA, CMS, AND OTHER COSTS TO IMPLEMENT THESE OPTIONS.
DISPLAY SPECIFIC NOTES:
1. SINGLE MODE FIBER WILL BE PROVIDED BY OTHERS BETWEEN COA NORTH (LED CMS LOCATION - COLOSSEO) AND COA EVENT LEVEL RACK ROOM. LED BIDDER SHALL EXTEND VIDEO, DATA, AND CONTROL SIGNALS TO LED HEADEND RACK ROOM FOR EACH LED DISPLAY.
2. IN BID PACKAGE (TBD), INCLUDE NEW LED CMS TYPE (TBD) TO PROVIDE CONTENT FOR THESE LED DISPLAYS, AND REPLACE LED CMS TYPE 1 (COLOSSEO). PROVIDE ALL CABLING AND ACCESSORIES. REMOVE LED CMS TYPE 1 AND ALL CABLING NO LONGER REQUIRED.